## Slide 1: A Step Ahead and A Step Behind
Lessons Learnt From Trialling a Prototype Patient-Led Internet-Based Cancer Care Self-Management System
Dr Gil Tidhar
Dr. Donna Milne, Lisa Sheeran, Matthew Holmes, Prof. Sanchia Aranda
Next

## Slide 2: CanCare: The Project
Background
  60% of Australians surviving at least 5 years after
  cancer diagnosis
  Cancer is now a chronic illness
  Variety of care settings and health providers
Aim
Trial a patient-led, internet based cancer
care coordination and self management
system to enhance the relationship and
communication between patients, family and
friends, and health professionals
Next

## Slide 3: Care Approach: Care Everywhere
Professional Carers
Non-Professional Carers
Family and Friends
Need 1
Need 2
Goal 1
Goal 2
Next

## Slide 4: Partnership and Support
Next

## Slide 5: Initial Interviews: Consumers and Health Professionals
Consumers:
  Significant demand for a patient-led internet-based cancer care self-management system.
  Capacity and desire to participate in the management of their care and in the care of someone they support.
Health Professionals:
  Recognize the potential benefits of patient-led care – to the patient and to the health system.
  Significant challenges with existing medical and hospital practices and existing care provider ICT.
  General concerns regarding changes to the care model.
Next

## Slide 6: Lessons Learnt: Considerations
Organizational and Contextual
Project Governance
Project Implementation
Next

## Slide 7: Organizational and Contextual Considerations
Develop, communicate, and share the trialed care model
Inclusion of health provider’s key decision makers
Ensure IT integration and support from health provider’s IT department
Next

## Slide 8: Project Governance Considerations
Next
Partnerships bring benefits but require compromise
Inclusive project management
Use clinical experts that understand IT systems and IT research
Manage gap between health provider IT and consumer IT environments
Reuse of existing IT systems reduces cost and risk but requires compromise

## Slide 9: Project Implementation Considerations
Next
Recruiting Users to the trial is critical to the success of the project
Expectations of reliability of trialed IT should be managed
New functionality should focus and be suitable for the patient and their carers

## Slide 10: Overall Lessons Learnt
Next
Patient-led cancer care self-management systems are:
A Step ahead of current medical and hospital practice
A Step behind consumer demand and requirements for uptake

## Slide 11
gil@seecare.net
www.seecare.net